## Project Tracker
Start Date | End Date | Module | Type | Improve Point / Bug | Status
N/A | N/A | General / Discussion | Bug | Discuss | Complete
2026-09-02 | 2026-09-02 | Auto-Update System | Improvement | Add auto-update, pre-update sync, and error reporting. | Complete
2026-09-02 | 2026-09-02 | Tracking Module | Improvement | It should show a Tracking active rather than both. | Complete
2026-09-02 | 2026-09-02 | Login Screen | Improvement | Make company logo dynamic on login. | Complete
2026-09-02 | 2026-09-02 | Tracking Module | Improvement | Add multi-user tracking requirements. | Complete
2026-09-02 | 2026-09-02 | Auto-Update System | Improvement | Add automatic application update system. | Complete
2026-09-02 | 2026-09-02 | Reporting / Excel Sheet | Improvement | Make an Excel sheet with all the points. | Complete
2026-09-02 | 2026-09-02 | Auto-Update System | Bug | Fix: make Windows EXE version updates dynamic and reliable. | Complete
2026-09-02 | 2026-09-02 | Tracking Module | Bug | Tracking and Start Tracking appear confusing because both relate to tracking. | Complete
2026-09-03 | 2026-09-03 | Dashboard / UI | Improvement | Make table size wider so application and activity timeline sections can occupy more horizontal space. | Complete
2026-09-03 | 2026-09-03 | Dashboard / Reporting | Improvement | Filters should be there and workday progress should also be shown at a percentage level, e.g. 51%. | Complete
2026-09-03 | 2026-09-03 | Login Screen | Improvement | Remove version on login page and fix company code verify icon / checkbox on login page / remove extra spacing. | Complete
2026-09-03 | 2026-09-03 | Log / Screenshot Module | Bug | When log is sent, make it configurable / screenshot; clean from local after upload. | Complete
2026-09-04 | 2026-09-04 | Idle Tracking | Improvement | Idle mention on that screen. | Complete
2026-09-04 | 2026-09-04 | Documentation | Improvement | Document update according to iHRMS Tracking. | Complete
2026-09-04 | 2026-09-04 | Tracking Module | Improvement | Productive applications count. | Complete
2026-09-04 | 2026-09-04 | Dashboard | Bug | Fixing in dashboard user/device popup. | Complete
2026-09-04 | 2026-09-04 | Dashboard / API | Bug | Logout can control with API; fix this in dashboard. | Complete
2026-09-07 | 2026-09-07 | Login / Tracking | Improvement | When login starts, tracking does not start after that. | Complete
2026-09-07 | 2026-09-07 | System Tray / UI | Improvement | In hidden icon, there is an option to show/exit. | Complete
2026-09-07 | 2026-09-07 | Application Stability | Bug | Not responding, shows exe file. | Complete
2026-09-07 | 2026-09-07 | Application Stability | Bug | There is some hang issue when starting. | Complete
2026-09-07 | 2026-09-07 | Idle Tracking | Bug | Fix the iHRMS Monitor idle/tracking state after Windows Sleep/Resume. | Complete
2026-09-07 | 2026-09-07 | Auto-Update System | Bug | Update issue: when background update starts, it should not loop. | Complete
2026-09-07 | 2026-09-07 | Idle Tracking / Backend | Bug | Idle time issue not updating in backend. | Complete
2026-09-08 | 2026-09-08 | Offline Log Sync | Bug | Offline log did not sent when application is online. | Complete
2026-09-08 | 2026-09-08 | Tracking / Log | Bug | Sametime not tracking the log when fresh start. | Complete
2026-09-08 | 2026-09-08 | Dashboard / UI | Bug | Dashboard facing issue like idle and more, some in UI. | Complete
2026-09-08 | 2026-09-08 | API / Sync | Bug | API syncs when show after connect not refresh and start sending. | Complete
2026-09-08 | 2026-09-08 | Dashboard / UI | Bug | Dashboard facing issue like application tracking name and today timeline , weekly timeline . | Complete
2026-09-08 | 2026-09-09 | EXE.File/Build | Bug | exe file show error after install the application | Complete
2026-09-08 | 2026-09-09 | test plan | Improvement | make a test cases then build the exe file and attache the report | Complete
2026-09-09 | 2026-09-09 | Dashboard / UI | Improvement | remove api syncs in dashboard | Complete
2026-09-09 | 2026-09-10 | Reporting mssg by mail | Improvement | when anything buddy uninstall appication send send on mssg at support online or offline | Complete
2026-09-09 | 2026-09-09 | api login | Improvement | iemi empty send im api or os_type send to backend | Complete
2026-09-09 | 2026-09-09 | Idle Tracking | Bug | idle send in window title show there | Complete
2026-09-09 | 2026-09-09 | version | Improvement | version log implement in application | Complete
2026-09-09 | 2026-09-09 | email error support | Bug | Fix Seqrite Email Protection for iHRMS Monitor | Complete
2026-09-10 | 2026-09-10 | Dashboard / UI/ API | Improvement | don’t show tracking application in dashboard | Complete
2026-09-10 | 2026-09-11 | Dashboard / UI/ API | Improvement | start time and attandance time , if not punch then show | Complete
2026-09-10 | 2026-09-10 | Dashboard / UI/ API | Improvement | user laptop health ,CPU,RAM/ and all | Complete
2026-09-10 | 2026-09-11 | Dashboard / UI/ API | Improvement | Do the task show the assigned task | Complete
2026-09-10 | 2026-09-15 | Login Screen | Improvement | add link to login in hrms | Complete
2026-09-10 | 2026-09-16 | API / Sync | Improvement | illegal app alter to backend | Pending
2026-09-14 | 2026-09-14 | Dashboard / UI | Bug | improve and assign task not load in dashborad | Complete
2026-09-14 | 2026-09-14 | Auto-Update System | Bug | after restart application re start the fail | Complete
2026-09-15 | 2026-09-15 | Dashboard / UI/ API | Bug | active time / punch time | Complete
2026-09-15 | 2026-09-15 | Dashboard / UI/ | Improvement | remove refresh / user, Sdevices | Complete
2026-09-15 | 2026-09-16 | Dashboard / UI/ | Improvement | add golbal logo with link redirect on that link | Complete
2026-09-15 | 2026-09-15 | Log / Screenshot Module | Bug | screenshot not upload in backend /db | Complete
2026-09-16 | 2026-09-16 | API / Sync | Bug | Not sending log on backend show device_token / 500 error on api | Complete
2026-09-18 | 2026-09-18 | API / Sync | Bug | Not sendng the log on backend | Complete
2026-09-18 | 2026-09-18 | Auto-Update System | Bug | Update issue: when background update starts, it should not loop. | Complete
2026-09-18 | 2026-09-18 | API / Sync | Bug | user laptop health ,CPU,RAM/ and all not syns in bakend | Complete
2026-09-18 | 2026-09-18 | Dashboard / UI/ | Improvement | remove the weekly timeline | Complete
2026-09-18 | 2026-09-18 | Dashboard / UI/ API | Improvement | add attandence mark and leaves balance | Complete
2026-09-18 | 2026-09-19 | Dashboard / UI/ API | Improvement | assign task add timesheet fill | Pending
2026-09-19 | 2026-09-19 | Dashboard / UI/ API | Bug | leaves balance leave type | Complete
2026-09-19 | 2026-09-19 | Dashboard / UI/ API | Bug | in dashboard attandence make calender view and improve more | Complete
2026-09-19 | 2026-09-21 | login in HRMS | Improvement | Auto login when user link on dashboard button add there global icon | Pending
2026-09-19 | 2026-09-19 | system health | Bug | round off thr number or digits syns then | Complete
2026-09-21 | 2026-09-21 | Dashboard / UI/ API / task fill | Bug | fill task has not work | Complete
2026-09-21 | 2026-09-21 | Dashboard / UI/ API /Leave balance | Bug | leaves balance leave type not load | Complete
2026-09-21 | 2026-09-21 | application name | Improvement | name change ihrms to workpulse | Complete
2026-09-22 | 2026-09-22 | Dashboard / UI/ | Improvement | add start and stop button like resume or paused | Complete
2026-09-22 |  | Dashboard / UI/ | Improvement | team content show in manager dashboard team online or offine | Pending
2026-09-23 | 2026-09-23 | Login Screen | Improvement | change Smart workspace activity monitoring To Smart workspace productivity monitoring and more too | Complete
2026-09-28 | 2026-09-28 | version /API | Improvement | update api change for compare version | Complete
2026-09-28 | 2026-09-28 | email error support | Improvement | fix the workflow of sending mail to support ihrms mail | Complete
2026-09-29 | 2026-09-30 | All module test by ai | Improvement | All module test by ai make a test cases then build the exe file and attache the report | Complete
2026-10-01 | 2026-10-01 | Dashboard / UI/ | Improvement | attandence card improve | Complete
2026-10-05 | 2026-10-05 | attandance api | Bug | not match api status of punching | Complete
2026-10-05 | 2026-10-05 | leave balance api | Bug | count of leaves not apply | Complete
2026-10-05 | 2026-10-05 | EXE.File/Build | Bug | not open sametimes hang | Complete
2026-10-05 | 2026-10-05 | Dashboard / UI/ | Bug | offline mention when net is off | Complete
2026-10-05 | 2026-10-05 | API / Sync | Improvement | when net is offline so done send mssg api not syns on support mail | Complete